## Technical Limit Drilling
Historical Drilling Perfomance | [43 empty] | Drilling Program
# | Rig | Well ID | 34" Section | 34" Depth | 34" FPD | 24" CSG | 24" CSG Depth | 24" CSG FPD | 22" Section | 22" Depth | 22" FPD | 18-5/8" CSG | 18-5/8" CSG Depth | 18-5/8" CSG FPD | 16" Section | 16" Depth | 16" FPD | 13-3/8" CSG | 13-3/8" CSG Depth | 13-3/8" CSG FPD | 12-1/4" Section | 12-1/4" Depth | 12-1/4" FPD | 9-5/8" CSG | 9-5/8" CSG Depth | 9-5/8" CSG FPD | 8-3/8" Section | 8-3/8" Depth | 8-3/8" FPD | 7" Liner/Casing | 7" Liner/Casing Depth | 7" Liner/Casing FPD | 6-1/8" Section | 6-1/8" Depth | 6-1/8" FPD | Spud to TD | TD to Release | Spud to Release | Tatweer Savings | Ensign Profit | Ensign Crew | Total Depth | Actual FPD | Well Design | Planned Days | Planned Depth | Planned FPD
1 | 1 | 1 | 2.3021 | 1630.04 | 708.0717 | 3.8333 | 1630.04 | 425.2278 | 3.6771 | 3165.04 | 417.4504 | 5.2812 | 3165.04 | 599.2975 | 7.9167 | 7464 | 543.0265 | 4.2604 | 7464 | 1751.9413 | 3.1458 | 9130 | 529.5894 | 5.0833 | 9130 | 1796.0656 | 6 | 11578 | 408 | 7.9583 | 11578 | 1454.8272 | 6.3229 | 13440 | 294.4843 | 55.6 | 22.4 | 78 |  |  |  | 13440 | 172.3077 | Vertical (0°) | 69 | 13291 | 192.6232
2 | 1 | 2 | 2.3229 | 1697 | 730.5471 | 2.5625 | 1697 | 662.2439 | 2.6875 | 3340 | 611.3488 | 3.8958 | 3340 | 857.3262 | 7.2188 | 7874 | 628.0866 | 4.8333 | 7874 | 1629.1034 | 2.0938 | 9617 | 832.4776 | 3.8125 | 9617 | 2522.4918 | 3.9375 | 12285 | 677.5873 | 15 | 12285 | 819 | 12.6979 | 14030 | 137.4241 | 62.2 | 14.6 | 76.8 |  |  |  | 14030 | 182.6823 | Deviated (20.79°) | 64 | 14110 | 220.4688
3 | 1 | 3 | 2.5312 | 1547 | 611.1605 | 10.2396 | 1547 | 151.0804 | 2.4479 | 2950 | 573.1404 | 27.5938 | 2950 | 106.9083 | 12.0833 | 7335 | 362.8966 | 3.75 | 7335 | 1956 | 3.375 | 9030 | 502.2222 | 4.9375 | 9030 | 1828.8608 | 2.3333 | 11513 | 1064.1429 | 4.3021 | 11513 | 2676.1453 | N/A | N/A | N/A | 69.2 | 7.4 | 76.6 |  |  |  | 11513 | 150.3003 | Deviated (20.48°) | 54.3 | 11596 | 213.5543
4 | 1 | 4 | 2.6562 | 1873 | 705.1294 | 4.1771 | 1873 | 448.399 | 3.8854 | 3463 | 409.2225 | 4.2083 | 3463 | 822.8911 | 12.0833 | 8290 | 399.4759 | 5.1875 | 8290 | 1598.0723 | 2.7708 | 10465 | 784.9624 | 4.0938 | 10465 | 2556.3359 | 4.8333 | 13336 | 594 | 10.125 | 13336 | 1317.1358 | 11.8646 | 15590 | 189.9772 | 65.9 | 15.5 | 81.4 |  |  |  | 15590 | 191.5233 | Deviated (25.90°) | 71 | 15250 | 214.7887
5 | 1 | 5 | 2.875 | 1581 | 549.913 | 1.875 | 1581 | 843.2 | 2.1458 | 3105 | 710.2136 | 2.875 | 3105 | 1080 | 5.4062 | 7272 | 770.7746 | 3.9688 | 7272 | 1832.315 | 1 | 8632 | 1360 | 3.3229 | 8632 | 2597.7179 | 15.9375 | 10092 | 91.6078 | 2.4792 | 10092 | 4070.7227 | N/A | N/A | N/A | 39.5 | 5.5 | 45 | #REF! | #REF! | #REF! | 10092 | 224.2667 | Vertical (0°) | 59 | 11070 | 187.6271
6 | 1 | 6 | 2.375 | 1842 | 775.5789 | 3.5208 | 1842 | 523.1716 | 3.5208 | 3579 | 493.3491 | 4.3958 | 3579 | 814.1801 | 7.1458 | 7952 | 611.965 | 4.8125 | 7952 | 1652.3636 | 1.7083 | 9742 | 1047.8049 | 3.5625 | 9742 | 2734.5965 | 4.5208 | 12220 | 548.129 | 3.2812 | 12220 | 3724.1905 | N/A | N/A | N/A | 35.6 | 6.1 | 41.7 | #REF! | #REF! | #REF! | 12220 | 293.0456 | Deviated (21.45°) | 61 | 12200 | 200
7 | 1 | 7 | 4.4479 | 1777 | 399.5129 | 2.1042 | 1777 | 844.5149 | 2.4896 | 3402 | 652.7197 | 3.4688 | 3402 | 980.7568 | 6.75 | 7942 | 672.5926 | 4.4062 | 7942 | 1802.4397 | 2.9896 | 10065 | 710.1324 | 3.625 | 10065 | 2776.5517 | 2.4688 | 12670 | 1055.1899 | 6.0312 | 12670 | 2100.7254 | N/A | N/A | N/A | 32.8 | 8.9 | 41.7 | #REF! | #REF! | #REF! | 12670 | 303.8369 | Deviated (12.38°) | 59.5 | 12744 | 214.1849
8 | 1 | 8 | 4.375 | 2060 | 470.8571 | 5.7083 | 2060 | 360.8759 | 4.3646 | 3741 | 385.1456 | 3.4479 | 3741 | 1085.003 | 11.3646 | 8222 | 394.2951 | 11.9792 | 8222 | 686.3583 | 2.8438 | 10192 | 692.7473 | 3.9688 | 10192 | 2568.063 | 3.3125 | 12920 | 823.5472 | 5.3438 | 12920 | 2417.7778 | N/A | N/A | N/A | 50.3 | 16.1 | 66.4 |  |  |  | 12920 | 194.5783 | Deviated (23.50°) | 71 | 14640 | 206.1972
9 | 1 | 9 | 2.6875 | 1950 | 725.5814 | 5.3854 | 1950 | 362.089 | 5.5208 | 3399 | 262.4604 | 4.8438 | 3399 | 701.729 | 9.5417 | 7427 | 422.1485 | 4.9271 | 7427 | 1507.3827 | 1.9896 | 9025 | 803.1832 | 3.7708 | 9025 | 2393.3702 | 4.4479 | 11525 | 562.0609 | 5.8958 | 11525 | 1954.7703 | N/A | N/A | N/A | 43.1 | 12.8 | 55.9 |  |  | #REF! | 11525 | 206.1717 | Deviated (12.73°) | 60.3 | 11571 | 191.8905
10 | 1 | 10 | 3.0208 | 1628 | 538.9241 | 2.4271 | 1628 | 670.7639 | 2.4062 | 3110 | 615.8961 | 3.8333 | 3110 | 811.3043 | 9.3333 | 7890 | 512.1429 | 11.9271 | 7890 | 661.5197 | 3.2083 | 9860 | 614.026 | 4.3021 | 9860 | 2291.9128 | 3.5417 | 12120 | 638.1176 | 5.0208 | 12120 | 2413.9419 | N/A | N/A | N/A | 44.4 | 7.8 | 52.2 | #REF! | #REF! | #REF! | 12120 | 232.1839 | Deviated (32.40°) | 59.5 | 12133 | 203.916
11 | 1 | 11 | 2.375 | 1661 | 699.3684 | 1.7396 | 1661 | 954.8263 | 1.7292 | 3032 | 792.8675 | 3.1562 | 3032 | 960.6337 | 5.8229 | 8170 | 882.3757 | 7.0729 | 8170 | 1155.1105 | 2.9271 | 10502 | 796.6975 | 4.2396 | 10502 | 2477.1302 | 8.3021 | 13150 | 318.9561 | 6.1354 | 13150 | 2143.2937 | N/A | N/A | N/A | 37.3 | 9.7 | 47 | #REF! | #REF! | #REF! | 13150 | 279.7872 | Deviated (36.89°) | 61 | 13400 | 219.6721
12 | 1 | 12 | 3.9792 | 1810 | 454.8691 | 1.8542 | 1810 | 976.1798 | 2.8333 | 3520 | 603.5294 | 3.0625 | 3520 | 1149.3878 | 7.375 | 8445 | 667.7966 | 4.125 | 8445 | 2047.2727 | 9.4688 | 10600 | 227.5908 | 6.3542 | 10600 | 1668.1967 | 3.7708 | 13302 | 716.5525 | 7.6771 | 13302 | 1732.6893 | 13.1667 | 15563 | 171.7215 | 64.2 | 12 | 76.2 |  |  |  | 15563 | 204.2388 | Deviated (27.99°) | 74 | 15203 | 205.4459
13 | 1 | 13 | 3.25 | 1712 | 526.7692 | 1.8021 | 1712 | 950.0116 | 2.6458 | 3255 | 583.1811 | 3.5417 | 3255 | 919.0588 | 9.1875 | 8099 | 527.2381 | 5.1562 | 8099 | 1570.7152 | 2.2083 | 9969 | 846.7925 | 3.9375 | 9969 | 2531.8095 | 2.1979 | 11696 | 785.7441 | 4.9062 | 11696 | 2383.8981 | N/A | N/A | N/A | 33.9 | 7.6 | 41.5 | #REF! | #REF! | #REF! | 11696 | 281.8313 | Deviated (30.90°) | 58.3 | 11800 | 202.4014
14 | 1 | 14 | 2.4375 | 1867 | 765.9487 | 1.7604 | 1867 | 1060.5444 | 2.2812 | 3445 | 691.726 | 2.625 | 3445 | 1312.381 | 9.3542 | 7840 | 469.8441 | 3.6458 | 7840 | 2150.4 | 1.9688 | 9662 | 925.4603 | 3.8021 | 9662 | 2541.2384 | 2.5521 | 12120 | 963.1347 | 3.3333 | 12120 | 3636 | N/A | N/A | N/A | 30.6 | 8.6 | 39.2 | #REF! | #REF! | #REF! | 12120 | 309.1837 | Deviated (10.12°) | 59.5 | 12400 | 208.4034
15 | 1 | 15 | 4.2708 | 1804 | 422.4 | 1.8542 | 1804 | 972.9438 | 2.8646 | 3433 | 568.6691 | 2.9583 | 3433 | 1160.4507 | 10.4792 | 7900 | 426.2744 | 4.7083 | 7900 | 1677.8761 | 2.6979 | 9857 | 725.3745 | 4.2188 | 9857 | 2336.4741 | 3.8125 | 12367 | 658.3607 | 6.1875 | 12367 | 1998.7071 | N/A | N/A | N/A | 37.8 | 8.9 | 46.7 | #REF! | #REF! | #REF! | 12367 | 264.818 | Deviated (11.45°) | 59.5 | 12230 | 205.5462
16 | 1 | 16 | 3.3021 | 1602 | 485.1483 | 13.6562 | 1602 | 117.3089 | 2.25 | 3119 | 674.2222 | 6.3125 | 3119 | 494.099 | 8.9375 | 7986 | 544.5594 | 4.3125 | 7986 | 1851.8261 | 4.7396 | 10300 | 488.2286 | 4.0833 | 10300 | 2522.449 | 6.5104 | 13935 | 558.336 | 4.0208 | 13935 | 3465.6995 | N/A | N/A | N/A | 48.8 | 7.7 | 56.5 | #REF! | #REF! | #REF! | 13935 | 246.6372 | Deviated (31.27°) | 59 | 13260 | 224.7458
17 | 2 | 17 | 3.7604 | 1627 | 432.6648 | 6.3646 | 1627 | 255.6334 | 3.3854 | 3070 | 426.24 | 4.3333 | 3070 | 708.4615 | 6.0208 | 7366 | 713.5225 | 6.0104 | 7366 | 1225.539 | 7.2292 | 9100 | 239.8617 | 4.5312 | 9100 | 2008.2759 | 2.6354 | 11570 | 937.2332 | 7.7708 | 11570 | 1488.9008 | N/A | N/A | N/A | 44.7 | 11.8 | 56.5 |  |  |  | 11571 | 204.7965 | Deviated (9.72°) | 61.6 | 11576 | 187.9221
18 | 2 | 18 | 3.6354 | 1585 | 435.9885 | 2.0312 | 1585 | 780.3077 | 2.4688 | 3148 | 633.1139 | 3.2917 | 3148 | 956.3544 | 5.6562 | 7370 | 746.4309 | 4.5 | 7370 | 1637.7778 | 1.2812 | 8748 | 1075.5122 | 3.4583 | 8748 | 2529.5422 | 2.0833 | 11140 | 1148.16 | 4.375 | 11140 | 2546.2857 | N/A | N/A | N/A | 27.8 | 7.5 | 35.3 | #REF! | #REF! | #REF! | 11140 | 315.5807 | Deviated (11.90°) | 67 | 11126 | 166.0597
19 | 2 | 19 | 3.4062 | 1513 | 444.1835 | 5.2083 | 1513 | 290.496 | 13.3438 | 2401 | 66.548 | 16.8229 | 2401 | 142.722 | 6.2083 | 7220 | 776.2148 | 4.4583 | 7220 | 1619.4393 | 2.5833 | 8970 | 677.4194 | 4.9479 | 8970 | 1812.8842 | 2.0104 | 11265 | 1141.5544 | 6.5104 | 11265 | 1730.304 | N/A | N/A | N/A | 58.8 | 10.2 | 69 |  |  |  | 11266 | 163.2754 | Vertical (0°) | 67.1 | 11258 | 167.7794
20 | 2 | 20 | 3.1042 | 1748 | 563.1141 | 5.3229 | 1748 | 328.3914 | 3.1458 | 3250 | 477.457 | 8.4167 | 3250 | 386.1386 | 4.9792 | 7498 | 853.1548 | 7.0312 | 7498 | 1066.3822 | 2.625 | 9210 | 652.1905 | 10.2292 | 9210 | 900.3666 | 8.8646 | 11586 | 268.0329 | 4.5729 | 11586 | 2533.6128 | N/A | N/A | N/A | 53.4 | 14 | 67.4 |  |  |  | 11586 | 171.8991 | Deviated (15.00°) | 52 | 11600 | 223.0769
21 | 2 | 21 | 4.7812 | 1988 | 415.7908 | 10.0521 | 1988 | 197.7699 | 5.0312 | 3770 | 354.1863 | 5.2604 | 3770 | 716.6733 | 11.3542 | 8430 | 410.422 | 6.1562 | 8430 | 1369.3401 | 2.8854 | 10520 | 724.3321 | 4.7396 | 10520 | 2219.6044 | 2.4062 | 12180 | 689.8701 | 9 | 12180 | 1353.3333 | N/A | N/A | N/A | 53 | 21.1 | 74.1 |  |  |  | 12180 | 164.3725 | Deviated (20.74°) | 78 | 15766 | 202.1282
22 | 2 | 22 | 3.5417 | 1549 | 437.3647 | 2.7083 | 1549 | 571.9385 | 1.6562 | 2511 | 580.8302 | 7.5104 | 2511 | 334.3356 | 6.4792 | 7658 | 794.3923 | 4.7292 | 7658 | 1619.3128 | 2.4167 | 9530 | 774.6207 | 3.8854 | 9530 | 2452.7614 | 3.2083 | 11800 | 707.5325 | 6.3021 | 11800 | 1872.3967 | N/A | N/A | N/A | 36.1 | 9.2 | 45.3 | #REF! | #REF! | #REF! | 11801 | 260.5077 | Deviated (24.29°) | 60.8 | 11930.75 | 196.2294
23 | 2 | 23 | 3.5417 | 1631 | 460.5176 | 2.4688 | 1631 | 660.6582 | 3.3021 | 3145 | 458.4984 | 4.2708 | 3145 | 736.3902 | 5.7708 | 7845 | 814.4404 | 5.2708 | 7845 | 1488.3794 | 2.4896 | 9833 | 798.5272 | 4.6979 | 9833 | 2093.0554 | 3.1042 | 12247 | 777.6644 | 5.8958 | 12247 | 2077.2297 | N/A | N/A | N/A | 35 | 13.2 | 48.2 | #REF! | #REF! | #REF! | 12247 | 254.0871 | Deviated (27.27°) | 67 | 12232 | 182.5672
24 | 2 | 24 | 3.5417 | 1518 | 428.6118 | 3.8854 | 1518 | 390.6917 | 2.9062 | 2889 | 471.7419 | 4.8333 | 2889 | 597.7241 | 5.9792 | 7144 | 711.6376 | 8.7396 | 7144 | 817.4303 | 2.1146 | 8662 | 717.8719 | 8.4062 | 8662 | 1030.4238 | 2.6875 | 10757 | 779.5349 | 5.5104 | 10757 | 1952.121 | N/A | N/A | N/A | 43.1 | 8.8 | 51.9 |  |  | #REF! | 10757 | 207.264 | Deviated (20.16°) | 61.5 | 11210 | 182.2764
25 | 2 | 25 | 4.1042 | 1805 | 439.797 | 2.1875 | 1805 | 825.1429 | 4.4792 | 3559 | 391.5907 | 4.8854 | 3559 | 728.4947 | 9.1354 | 7932 | 478.6864 | 3.8021 | 7932 | 2086.2247 | 2.7188 | 9745 | 666.8506 | 3.5833 | 9745 | 2719.5349 | 2.5625 | 12218 | 965.0732 | 3.5521 | 12218 | 3439.6716 | N/A | N/A | N/A | 38.07 | 7.58 | 45.65 | #REF! | #REF! | #REF! | 12218 | 267.6451 | Vertical (0°) | 60.8 | 12279 | 201.9572
26 | 2 | 26 | 2.6458 | 1521 | 574.8661 | 6.3542 | 1521 | 239.3705 | 2.1042 | 2984 | 695.2871 | 6.7708 | 2984 | 440.7138 | 5.6875 | 7084 | 720.8791 | 6.0833 | 7084 | 1164.4932 | 1.3021 | 8352 | 973.824 | 4.2396 | 8352 | 1970.0049 | 3.1042 | 10715 | 761.2349 | 4.8646 | 10715 | 2202.6552 | 82.2812 | 12827 | 25.6681 | 125.3 | 25.7 | 151 |  |  |  | 12827 | 84.947
27 | 1 | 27 | 2.5521 | 1525 | 597.551 | 7.8333 | 1525 | 194.6809 | 3.6979 | 2900 | 371.831 | 4.4375 | 2900 | 653.5211 | 6.0208 | 7092 | 696.2491 | 5.0833 | 7092 | 1395.1475 | 2.1042 | 8736 | 781.3069 | 4.6042 | 8736 | 1897.4118 | 6.1042 | 10940 | 361.0648 | 15.8021 | 10940 | 692.3138 | 27.6667 | 12530 | 57.4699 | 85.8 | 21.1 | 106.9 |  |  |  | 12530 | 117.2123 | Deviated (22.6°) | 139 | 14164 | 101.8993
28 | 2 | 28 | 3.8646 | 1635.46 | 423.1918 | 2.2812 | 1635.46 | 716.914 | 2.8125 | 3090 | 517.1698 | 3.1042 | 3090 | 995.4362 | 6.5521 | 7277 | 639.0334 | 3.7604 | 7277 | 1935.1579 | 23.125 | 11195 | 169.427 | 4.75 | 11195 | 2356.8421 | N/A | N/A | N/A | N/A | N/A | N/A | 3.5938 | 12210 | 282.4348 | 53.8 | 12.8 | 66.6 |  |  |  | 12210 | 183.3333 | Vertical (0°) | 125 | 15637.96 | 125.1037
29 | 2 | 29 | 4 | 1505.26 | 376.315 | 2.25 | 1505.26 | 669.0044 | 2.3125 | 2847 | 580.2119 | 3.2396 | 2847 | 878.8167 | 5.7917 | 7047 | 725.1799 | 3.7396 | 7047 | 1884.4345 | 15.9792 | 11100 | 253.6428 | 10.2604 | 11100 | 1081.8274 | 10.2604 | 13230 | 207.5939 | 15.6771 | 13230 | 843.907 | N/A | N/A | N/A | 56.9 | 28.8 | 85.7 |  |  |  | 13232 | 154.3991 | Deviated (45°) | 80 | 13417.92 | 167.724
30 | 2 | 30 | 4.2812 | 1525 | 356.2044 | 2.5 | 1525 | 610 | 2.9479 | 2875 | 457.9505 | 3.7708 | 2875 | 762.4309 | 15.8438 | 6965 | 258.146 | 4.0104 | 6965 | 1736.7273 | 19.6771 | 10790 | 194.3886 | 7.3125 | 10790 | 1475.5556 | 9.5938 | 12320 | 159.4788 | 5.4896 | 12320 | 2244.2505 | N/A | N/A | N/A | 69.8 | 11.1 | 80.9 |  |  |  | 12320 | 152.2868 | Vertical (0°) | 75 | 12208 | 162.7733
31 | 1 | 31 | 3.0625 | 1642 | 536.1633 | 1.7188 | 1642 | 955.3455 | 2.6146 | 3127 | 567.9681 | 3.1875 | 3127 | 981.0196 | 5.8125 | 7427 | 739.7849 | 4.0938 | 7427 | 1814.229 | 15.6667 | 11513 | 260.8085 | 8.9896 | 11513 | 1280.7045 | 27.2292 | 11875 | 13.2946 | 5.9583 | 11875 | 1993.007 | 19.5208 | 17550 | 290.715 | 98.11 | 9.15 | 107.26 |  |  |  | 17550 | 163.6211 | Horizontal (86°) | 75 | 15738 | 209.84
32 | 2 | 32 | 3.6354 | 1578.28 | 434.1401 | 2.5312 | 1578.28 | 623.518 | 1.9688 | 3035 | 739.9213 | 3.1667 | 3035 | 958.4211 | 5.4271 | 7240 | 774.8177 | 3.8125 | 7240 | 1899.0164 | 22.0938 | 11285 | 183.0835 | 5.0521 | 11285 | 2233.732 | 5.1771 | 13264 | 382.2616 | 12.6771 | 13264 | 1046.2975 | N/A | N/A | N/A | 52.8 | 17.8 | 70.6 |  |  |  | 13265 | 187.8895 | Horizontal (90°) | 75 | 15459 | 206.12
33 | 2 | 33 | 3.2812 | 1512 | 460.8 | 2.0312 | 1512 | 744.3692 | 2.5312 | 2881 | 540.8395 | 3.9688 | 2881 | 725.9213 | 4.9583 | 7158 | 862.5882 | 4.0417 | 7158 | 1771.0515 | 17.3958 | 10890 | 214.5341 | 5.1979 | 10890 | 2095.0701 | 3.3542 | 12320 | 426.3354 | 8.6771 | 12320 | 1419.8319 | N/A | N/A | N/A | 46.7 | 13 | 59.7 |  |  |  | 12320 | 206.3652 | Deviated (18.3°) | 75 | 12289 | 163.8533
34 | 1 | 34 | 2.6042 | 1548 | 594.432 | 1.7083 | 1548 | 906.1463 | 2.3125 | 2932 | 598.4865 | 4.7812 | 2932 | 613.2288 | 7.0625 | 7057 | 584.0708 | 4.3542 | 7057 | 1620.7464 | 23.8021 | 11260 | 176.5812 | 4.5208 | 11260 | 2490.6912 | 4.9375 | 13100 | 372.6582 | 5.8438 | 13100 | 2241.7112 | N/A | N/A | N/A | 56 | 8.2 | 64.2 |  |  |  | 13100 | 204.0498 | Horizontal (90°) | 75 | 16567 | 220.8933
35 | 2 | 35 | 2.6042 | 1546.15 | 593.7216 | 2.1042 | 1546.15 | 734.804 | 2.3333 | 2922 | 589.65 | 3.1146 | 2922 | 938.1672 | 4.7812 | 7170 | 888.4706 | 3.8542 | 7170 | 1860.3243 | 17.9896 | 10830 | 203.4511 | 5.2917 | 10830 | 2046.6142 | 4.1562 | 12382 | 373.4135 | 9.5104 | 12382 | 1301.9409 | N/A | N/A | N/A | 46.2 | 17 | 63.2 |  |  |  | 12382 | 195.9177 | Deviated (11.2°) | 75 | 12399 | 165.32
36 | 1 | 36 | 3.3854 | 1507 | 445.1446 | 1.9375 | 1507 | 777.8065 | 1.9583 | 2947 | 735.3191 | 3.1979 | 2947 | 921.5375 | 5.0833 | 7058 | 808.7213 | 3.7708 | 7058 | 1871.7348 | 17.9792 | 10762 | 206.0162 | 6.7292 | 10762 | 1599.3065 | 3.6667 | 12236 | 402 | 4.9167 | 12236 | 2488.678 | 3.8125 | 14075 | 482.3607 | 56.47 | 47.67 | 104.14 |  |  |  | 14075 | 135.1546 | Horizontal (90°) | 75 | 17265 | 230.2
37 | 2 | 37 | 3.4688 | 1638 | 472.2162 | 1.6562 | 1638 | 988.9811 | 2.2708 | 3201 | 688.2936 | 2.7604 | 3201 | 1159.6075 | 3.9896 | 7535 | 1086.329 | 4.0208 | 7535 | 1873.9896 | 23.7917 | 11815 | 179.8949 | 6.0208 | 11815 | 1962.3529 | 4.8438 | 13970 | 444.9032 | 12.9271 | 13970 | 1080.6769 | 18.6562 | 16000 | 108.8107 | 84.51 | 15.13 | 99.64 |  |  |  | 16000 | 160.5781 | Vertical (0°) | 75 | 13796 | 183.9467
38 | 1 | 38 | 2.0208 | 1552 | 768 | 1.8854 | 1552 | 823.1602 | 2.0312 | 2990 | 707.9385 | 3.6458 | 2990 | 820.1143 | 6.2604 | 7121 | 659.8602 | 3.4271 | 7121 | 2077.8602 | 17.2604 | 11040 | 227.0513 | 4.125 | 11040 | 2676.3636 | N/A | N/A | N/A | N/A | N/A | N/A | 2.6458 | 12710 | 631.1811 | 43.3 | 5.8 | 49.1 |  |  |  | 12710 | 258.8595 | Vertical (0°) | 75 | 12710 | 169.4667
39 | 2 | 39 | 2.4792 | 1625 | 655.4622 | 1.9583 | 1625 | 829.7872 | 1.8438 | 3190 | 848.8136 | 3 | 3190 | 1063.3333 | 5.4375 | 7360 | 766.8966 | 3.1667 | 7360 | 2324.2105 | 17.1979 | 11131 | 219.2707 | 4.1562 | 11131 | 2678.1353 | N/A | N/A | N/A | N/A | N/A | N/A | 4.8125 | 12940 | 375.8961 | 44 | 9 | 53 |  |  |  | 12940 | 244.1509 | Vertical (0°) | 75 | 12947 | 172.6267
40 | 1 | 40 | 1.3333 | 1520 | 1140 | 1.5417 | 1520 | 985.9459 | 1.7396 | 2874 | 778.3473 | 5.0625 | 2874 | 567.7037 | 4.6979 | 6975 | 872.9401 | 3.1875 | 6975 | 2188.2353 | 0.91667 | 8260 | 1401.8182 | 4.1354 | 8260 | 1997.3804 | 2.4896 | 10900 | 1060.4184 | 4.0417 | 10900 | 2696.9072 | 1.8229 | 12792 | 1037.8971 | 31 | 5.9 | 36.9 |  |  |  | 12792 | 346.6667 | Horizontal (85°) | 75 | 17046 | 227.28
41 | 2 | 41 | 1.7083 | 1520 | 889.7561 | 3.0729 | 1520 | 494.6441 | 1.4479 | 2858 | 924.0863 | 3.3021 | 2858 | 865.5142 | 1.8438 | 7060 | 2279.0508 | 4.0625 | 7060 | 1737.8462 | 2.9792 | 8350 | 433.007 | 5.8438 | 8350 | 1428.877 | 1.7083 | 10820 | 1445.8537 | 3.6875 | 10820 | 2934.2373 | 1.2604 | 12146 | 1052.0331 | 67.4 | 6.1 | 73.5 |  |  |  | 12146 | 165.2517 | Deviated (20.00°) | 75 | 12369 | 164.92
42 | 1 | 42 | 1.3229 | 1620 | 1224.5669 | 2.1562 | 1620 | 751.3043 | 1.9896 | 3112 | 749.9058 | 4.7396 | 3112 | 656.5978 | 2.8542 | 7256 | 1451.9124 | 4.3125 | 7256 | 1682.5507 | 0.89583 | 8762 | 1681.1163 | 3.3542 | 8762 | 2612.2733 | 9.8125 | 11220 | 250.4968 | 5.8333 | 11220 | 1923.4286 | 11 | 17008 | 526.1818 | 48.09 | 12.9 | 60.99 |  |  |  | 17013 | 278.9474 | Horizontal (88.67°) | 75 | 17622 | 234.96
43 | 1 | 43 | 1.8542 | 1512 | 815.4607 | 3.7396 | 1512 | 404.3231 | 1.2396 | 3017 | 1214.1176 | 4.625 | 3017 | 652.3243 | 2.875 | 7257 | 1474.7826 | 3.3229 | 7257 | 2183.9248 | 1.2083 | 8852 | 1320 | 3.3125 | 8852 | 2672.3019 | 3.375 | 11216 | 700.4444 | 2.3646 | 11216 | 4743.3304 | 2.8438 | 13018 | 633.6703 | 31.3 | 5.9 | 37.2 |  |  |  | 13018 | 349.9462 | Deviated (11.44°) | 48 | 12909 | 268.9375
44 | 2 | 44 | 2.2292 | 1529 | 685.9065 | 5.1042 | 1529 | 299.5592 | 1.9375 | 2961 | 739.0968 | 3.1042 | 2961 | 953.8792 | 1.9792 | 7132 | 2107.4526 | 4.4167 | 7132 | 1614.7925 | 2.8125 | 8864 | 615.8222 | 7.6042 | 8864 | 1165.6767 | 3.4375 | 11225 | 686.8364 | 2.8333 | 11225 | 3961.7647 | 4.7708 | 13175 | 408.7336 | 40.23 | 7.8 | 48.03 |  |  |  | 13175 | 274.3077 | Deviated (12.68°) | 35 | 13092 | 374.0571
45 | 1 | 45 | 2.2812 | 1445 | 633.4247 | 2.0833 | 1445 | 693.6 | 1.2188 | 2672 | 1006.7692 | 2.9062 | 2672 | 919.3978 | 5.6042 | 6232 | 635.2416 | 3.3438 | 6232 | 1863.7757 | 7.0938 | 8349 | 298.4317 | 3.3438 | 8349 | 2496.8972 | 51.6458 | 15981 | 147.7757 | 2.9792 | 15981 | 5364.2517 | 4.5625 | 16322 | 74.7397 | 86.71 | 2.63 | 89.34 |  |  |  | 16322 | 182.6953 | Horizontal (87.28°) | 38 | 16173 | 425.6053
46 | 2 | 46 | 1.7708 | 1564 | 883.2 | 3.6667 | 1564 | 426.5455 | 19.1042 | 2904 | 70.1418 | 2.9167 | 2904 | 995.6571 | 2.8542 | 7152 | 1488.3504 | 3.125 | 7152 | 2288.64 | 0.72917 | 8513 | 1866.5143 | 2.4375 | 8513 | 3492.5128 | 1.6771 | 10716 | 1313.5901 | 2.5104 | 10716 | 4268.6141 | 26.7812 | 12520 | 67.3606 | 68.08 | 7.43 | 75.51 |  |  |  | 12520 | 165.8059 | Deviated (17.17°) | 45 | 12516 | 278.1333
47 | 1 | 47 | 2.5 | 1575 | 630 | 2.0938 | 1575 | 752.2388 | 1.5729 | 3123 | 984.1589 | 3.3229 | 3123 | 939.837 | 2.7396 | 7315 | 1530.1597 | 3.375 | 7315 | 2167.4074 | 3.75 | 8636 | 352.2667 | 4.8021 | 8636 | 1798.3861 | 1.4271 | 11108 | 1732.2044 | 3.1146 | 11108 | 3566.4482 | 25.8229 | 17552 | 249.5458 | 54.4 | 11.6 | 66 |  |  |  | 17552 | 265.9394 | Deviated (16.01°) | 45 | 12666 | 281.4667
48 | 1 | 48 | 1.4271 | 1581 | 1107.854 | 2.1875 | 1581 | 722.7429 | 1.4375 | 3075 | 1039.3043 | 3.4375 | 3075 | 894.5455 | 2.5208 | 7250 | 1656.1983 | 3.375 | 7250 | 2148.1481 | 2.9375 | 8670 | 483.4043 | 3.7083 | 8670 | 2337.9775 | 3.2396 | 11317 | 817.0804 | 3.1146 | 11317 | 3633.5518 | 1.7604 | 13085 | 1004.3077 | 29.15 | 3.82 | 32.97 |  |  |  | 13085 | 396.8759 | Deviated (37.14°) | 45 | 13055 | 290.1111
49 | 2 | 49 | 1.5729 | 1599 | 1016.5828 | 2.0208 | 1599 | 791.2577 | 1.7604 | 3100 | 852.6391 | 2.8229 | 3100 | 1098.155 | 3.25 | 7237 | 1272.9231 | 2.9375 | 7237 | 2463.6596 | 1.4688 | 8550 | 893.9574 | 3.2812 | 8550 | 2605.7143 | 1.7812 | 11142 | 1455.1579 | 2.4792 | 11142 | 4494.2521 | 1.3542 | 12805 | 1228.0615 | 24.73 | 3.46 | 28.19 |  |  |  | 12805 | 454.2391 | Deviated (27.65°) | 45 | 12814 | 284.7556
50 | 2 | 50 | 1.1562 | 1766 | 1527.3514 | 0.72917 | 1766 | 2421.9429 | N/A | 1766 | N/A | 1.9479 | 1766 | 906.6096 | 4.0208 | 7540 | 1436.0207 | 4.1771 | 7540 | 1805.0873 | 3.0312 | 9200 | 547.6289 | 4.4167 | 9200 | 2083.0189 | 8.4375 | 11738 | 300.8 | 2.8958 | 11738 | 4053.4101 | 17.1354 | 14864 | 182.4292 | 48.1 | 8.2 | 56.3 |  |  |  | 14864 | 264.0142 | Horizontal (89.50°) | 45 | 15045 | 334.3333
51 | 1 | 51 | 1.7188 | 1532 | 891.3455 | 2.1562 | 1532 | 710.4928 | 1.4375 | 2950 | 986.4348 | 3.8958 | 2950 | 757.2193 | 6.0833 | 7822 | 800.8767 | 3.9062 | 7822 | 2002.432 | 3.2604 | 9832 | 616.4856 | 2.9688 | 9832 | 3311.8316 | 2.5625 | 12445 | 1019.7073 | 4.7396 | 12445 | 2625.7582 | N/A | N/A | N/A | 31 | 3.1 | 34.1 |  |  |  | 12339 | 361.8475 | Deviated (5.22°) | 40 | 12514 | 312.85
52 | 2 | 52 | 1.5312 | 1655 | 1080.8163 | 0.58333 | 1655 | 2837.1429 | N/A | 1655 | N/A | 0.91667 | 1655 | 1805.4545 | 5.0833 | 7715 | 1192.1311 | 3.9688 | 7715 | 1943.937 | 3.2188 | 10195 | 770.4854 | 2.9583 | 10195 | 3446.1972 | 1.7604 | 11470 | 724.2604 | 4.0312 | 11470 | 2845.2713 | 2.0208 | 13350 | 930.3093 | 26.1 | 5 | 31.1 |  |  |  | 13550 | 435.6913 | Horizontal (80.49°) | 45 | 12942 | 287.6
Note on V30: Adam Muller: Including 12-1/4"x14-3/4" & 10-5/8"x 12-1/4" hole opening sections

## IADC Data
# | Rig | Well ID | 34" Start | 34" End | 34" Duration | 34" Depth | 24" Start | 24" End | 24" Duration | 22" Start | 22" End | 22" Duration | 22" Depth | 18-5/8" Start | 18-5/8" End | 18-5/8" Duration | 16" Start | 16" End | 16" Duration | 16" Depth | 13-3/8" Start | 13-3/8" End | 13-3/8" Duration | 12-1/4" Start | 12-1/4" End | 12-1/4" Duration | 12-1/4" Depth | 9-5/8" Start | 9-5/8" End | 9-5/8" Duration | 8-3/8" Start | 8-3/8" End | 8-3/8" Duration | 8-3/8" Depth | 7" Start | 7" End | 7" Duration | 6-1/8" Start | 6-1/8" End | 6-1/8" Duration | 6-1/8" Depth | Spud to Start 12-1/4" | 12-1/4" to 6-1/8"
1 | 601 | KHUFF-A1760 | 2020-03-05 01:30 | 2020-03-07 08:45 | 2.3021 | 1630.04 | 2020-03-07 08:45 | 2020-03-11 04:45 | 3.8333 | 2020-03-11 04:45 | 2020-03-14 21:00 | 3.6771 | 3165.04 | 2020-03-14 21:00 | 2020-03-20 03:45 | 5.2812 | 2020-03-20 03:45 | 2020-03-28 01:45 | 7.9167 | 7464 | 2020-03-28 01:45 | 2020-04-01 08:00 | 4.2604 | 2020-04-01 08:00 | 2020-04-04 11:30 | 3.1458 | 9130 | 2020-04-04 11:30 | 2020-04-09 13:30 | 5.0833 | 2020-04-09 13:30 | 2020-04-15 13:30 | 6 | 11578 | 2020-04-15 13:30 | 2020-04-23 12:30 | 7.9583 | 2020-04-23 12:30 | 2020-04-29 20:15 | 6.3229 | 13440 | 27.2708 | 22.1875
2 | 601 | KHUFF-A1762 | 2020-05-29 20:45 | 2020-06-01 04:30 | 2.3229 | 1697 | 2020-06-01 04:30 | 2020-06-03 18:00 | 2.5625 | 2020-06-03 18:00 | 2020-06-06 10:30 | 2.6875 | 3340 | 2020-06-06 10:30 | 2020-06-10 08:00 | 3.8958 | 2020-06-10 08:00 | 2020-06-17 13:15 | 7.2188 | 7874 | 2020-06-17 13:15 | 2020-06-22 09:15 | 4.8333 | 2020-06-22 09:15 | 2020-06-24 11:30 | 2.0938 | 9617 | 2020-06-24 11:30 | 2020-06-28 07:00 | 3.8125 | 2020-06-28 07:00 | 2020-07-02 05:30 | 3.9375 | 12285 | 2020-07-02 05:30 | 2020-07-17 05:30 | 15 | 2020-07-17 05:30 | 2020-07-29 22:15 | 12.6979 | 14030 | 23.5208 | 24.8438
3 | 601 | KHUFF-A1904 | 2021-01-14 02:00 | 2021-01-16 14:45 | 2.5312 | 1547 | 2021-01-16 14:45 | 2021-01-26 20:30 | 10.2396 | 2021-01-26 20:30 | 2021-01-29 07:15 | 2.4479 | 2950 | 2021-01-29 07:15 | 2021-02-25 21:30 | 27.5938 | 2021-02-25 21:30 | 2021-03-09 23:30 | 12.0833 | 7335 | 2021-03-09 23:30 | 2021-03-13 17:30 | 3.75 | 2021-03-13 17:30 | 2021-03-17 02:30 | 3.375 | 9030 | 2021-03-17 02:30 | 2021-03-22 01:00 | 4.9375 | 2021-03-22 01:00 | 2021-03-24 09:00 | 2.3333 | 11513 | 2021-03-24 09:00 | 2021-03-28 16:15 | 4.3021 | N/A | N/A | N/A | N/A | 58.6458
4 | 601 | KHUFF-A1906 | 2020-08-21 14:00 | 2020-08-24 05:45 | 2.6562 | 1873 | 2020-08-24 05:45 | 2020-08-28 10:00 | 4.1771 | 2020-08-28 10:00 | 2020-09-01 07:15 | 3.8854 | 3463 | 2020-09-01 07:15 | 2020-09-05 12:15 | 4.2083 | 2020-09-05 12:15 | 2020-09-17 14:15 | 12.0833 | 8290 | 2020-09-17 14:15 | 2020-09-22 18:45 | 5.1875 | 2020-09-22 18:45 | 2020-09-25 13:15 | 2.7708 | 10465 | 2020-09-25 13:15 | 2020-09-29 15:30 | 4.0938 | 2020-09-29 15:30 | 2020-10-04 11:30 | 4.8333 | 13336 | 2020-10-04 11:30 | 2020-10-14 14:30 | 10.125 | 2020-10-14 14:30 | 2020-10-26 11:15 | 11.8646 | 15590 | 32.1979 | 21.8229
5 | 601 | KHUFF-A1908 | 2022-03-13 08:30 | 2022-03-16 05:30 | 2.875 | 1581 | 2022-03-16 05:30 | 2022-03-18 02:30 | 1.875 | 2022-03-18 02:30 | 2022-03-20 06:00 | 2.1458 | 3105 | 2022-03-20 06:00 | 2022-03-23 03:00 | 2.875 | 2022-03-23 03:00 | 2022-03-28 12:45 | 5.4062 | 7272 | 2022-03-28 12:45 | 2022-04-01 12:00 | 3.9688 | 2022-04-01 12:00 | 2022-04-02 12:00 | 1 | 8632 | 2022-04-02 12:00 | 2022-04-05 19:45 | 3.3229 | 2022-04-05 19:45 | 2022-04-21 18:15 | 15.9375 | 10092 | 2022-04-21 18:15 | 2022-04-24 05:45 | 2.4792 | N/A | N/A | N/A | N/A | 19.1458
6 | 601 | KHUFF-A1909 | 2021-08-18 09:00 | 2021-08-20 18:00 | 2.375 | 1842 | 2021-08-20 18:00 | 2021-08-24 06:30 | 3.5208 | 2021-08-24 06:30 | 2021-08-27 19:00 | 3.5208 | 3579 | 2021-08-27 19:00 | 2021-09-01 04:30 | 4.3958 | 2021-09-01 04:30 | 2021-09-08 08:00 | 7.1458 | 7952 | 2021-09-08 08:00 | 2021-09-13 03:30 | 4.8125 | 2021-09-13 03:30 | 2021-09-14 20:30 | 1.7083 | 9742 | 2021-09-14 20:30 | 2021-09-18 10:00 | 3.5625 | 2021-09-18 10:00 | 2021-09-22 22:30 | 4.5208 | 12220 | 2021-09-22 22:30 | 2021-09-26 05:15 | 3.2812 | N/A | N/A | N/A | N/A | 25.7708
7 | 601 | KHUFF-A1974 | 2021-11-27 14:15 | 2021-12-02 01:00 | 4.4479 | 1777 | 2021-12-02 01:00 | 2021-12-04 03:30 | 2.1042 | 2021-12-04 03:30 | 2021-12-06 15:15 | 2.4896 | 3402 | 2021-12-06 15:15 | 2021-12-10 02:30 | 3.4688 | 2021-12-10 02:30 | 2021-12-16 20:30 | 6.75 | 7942 | 2021-12-16 20:30 | 2021-12-21 06:15 | 4.4062 | 2021-12-21 06:15 | 2021-12-24 06:00 | 2.9896 | 10065 | 2021-12-24 06:00 | 2021-12-27 21:00 | 3.625 | 2021-12-27 21:00 | 2021-12-30 08:15 | 2.4688 | 12670 | 2021-12-30 08:15 | 2022-01-05 09:00 | 6.0312 | N/A | N/A | N/A | N/A | 23.6667
8 | 601 | KHUFF-A2131 | 2021-04-05 01:45 | 2021-04-09 10:45 | 4.375 | 2060 | 2021-04-09 10:45 | 2021-04-15 03:45 | 5.7083 | 2021-04-15 03:45 | 2021-04-19 12:30 | 4.3646 | 3741 | 2021-04-19 12:30 | 2021-04-22 23:15 | 3.4479 | 2021-04-22 23:15 | 2021-05-04 08:00 | 11.3646 | 8222 | 2021-05-04 08:00 | 2021-05-16 07:30 | 11.9792 | 2021-05-16 07:30 | 2021-05-19 03:45 | 2.8438 | 10192 | 2021-05-19 03:45 | 2021-05-23 03:00 | 3.9688 | 2021-05-23 03:00 | 2021-05-26 10:30 | 3.3125 | 12920 | 2021-05-26 10:30 | 2021-05-31 18:45 | 5.3438 | N/A | N/A | N/A | N/A | 41.2396
9 | 601 | KHUFF-A2145 | 2021-06-17 15:00 | 2021-06-20 07:30 | 2.6875 | 1950 | 2021-06-20 07:30 | 2021-06-25 16:45 | 5.3854 | 2021-06-25 16:45 | 2021-07-01 05:15 | 5.5208 | 3399 | 2021-07-01 05:15 | 2021-07-06 01:30 | 4.8438 | 2021-07-06 01:30 | 2021-07-15 14:30 | 9.5417 | 7427 | 2021-07-15 14:30 | 2021-07-20 12:45 | 4.9271 | 2021-07-20 12:45 | 2021-07-22 12:30 | 1.9896 | 9025 | 2021-07-22 12:30 | 2021-07-26 07:00 | 3.7708 | 2021-07-26 07:00 | 2021-07-30 17:45 | 4.4479 | 11525 | 2021-07-30 17:45 | 2021-08-05 15:15 | 5.8958 | N/A | N/A | N/A | N/A | 32.9062
10 | 601 | KHUFF-A2147 | 2022-01-14 10:00 | 2022-01-17 10:30 | 3.0208 | 1628 | 2022-01-17 10:30 | 2022-01-19 20:45 | 2.4271 | 2022-01-19 20:45 | 2022-01-22 06:30 | 2.4062 | 3110 | 2022-01-22 06:30 | 2022-01-26 02:30 | 3.8333 | 2022-01-26 02:30 | 2022-02-04 10:30 | 9.3333 | 7890 | 2022-02-04 10:30 | 2022-02-16 08:45 | 11.9271 | 2022-02-16 08:45 | 2022-02-19 13:45 | 3.2083 | 9860 | 2022-02-19 13:45 | 2022-02-23 21:00 | 4.3021 | 2022-02-23 21:00 | 2022-02-27 10:00 | 3.5417 | 12120 | 2022-02-27 10:00 | 2022-03-04 10:30 | 5.0208 | N/A | N/A | N/A | N/A | 32.9479
11 | 601 | KHUFF-A2149 | 2021-10-04 17:00 | 2021-10-07 02:00 | 2.375 | 1661 | 2021-10-07 02:00 | 2021-10-08 19:45 | 1.7396 | 2021-10-08 19:45 | 2021-10-10 13:15 | 1.7292 | 3032 | 2021-10-10 13:15 | 2021-10-13 17:00 | 3.1562 | 2021-10-13 17:00 | 2021-10-19 12:45 | 5.8229 | 8170 | 2021-10-19 12:45 | 2021-10-26 14:30 | 7.0729 | 2021-10-26 14:30 | 2021-10-29 12:45 | 2.9271 | 10502 | 2021-10-29 12:45 | 2021-11-02 18:30 | 4.2396 | 2021-11-02 18:30 | 2021-11-11 01:45 | 8.3021 | 13150 | 2021-11-11 01:45 | 2021-11-17 05:00 | 6.1354 | N/A | N/A | N/A | N/A | 21.8958
12 | 601 | KHUFF-A2234 | 2022-06-17 06:30 | 2022-06-21 06:00 | 3.9792 | 1810 | 2022-06-21 06:00 | 2022-06-23 02:30 | 1.8542 | 2022-06-23 02:30 | 2022-06-25 22:30 | 2.8333 | 3520 | 2022-06-25 22:30 | 2022-06-29 | 3.0625 | 2022-06-29 | 2022-07-06 09:00 | 7.375 | 8445 | 2022-07-06 09:00 | 2022-07-10 12:00 | 4.125 | 2022-07-10 12:00 | 2022-07-19 23:15 | 9.4688 | 10600 | 2022-07-19 23:15 | 2022-07-26 07:45 | 6.3542 | 2022-07-26 07:45 | 2022-07-30 02:15 | 3.7708 | 13302 | 2022-07-30 02:15 | 2022-08-06 18:30 | 7.6771 | 2022-08-06 18:30 | 2022-08-19 22:30 | 13.1667 | 15563 | 23.2292 | 27.2708
13 | 601 | KHUFF-A2407 | 2023-01-05 21:00 | 2023-01-09 03:00 | 3.25 | 1712 | 2023-01-09 03:00 | 2023-01-10 22:15 | 1.8021 | 2023-01-10 22:15 | 2023-01-13 13:45 | 2.6458 | 3255 | 2023-01-13 13:45 | 2023-01-17 02:45 | 3.5417 | 2023-01-17 02:45 | 2023-01-26 07:15 | 9.1875 | 8099 | 2023-01-26 07:15 | 2023-01-31 11:00 | 5.1562 | 2023-01-31 11:00 | 2023-02-02 16:00 | 2.2083 | 9969 | 2023-02-02 16:00 | 2023-02-06 14:30 | 3.9375 | 2023-02-06 14:30 | 2023-02-08 19:15 | 2.1979 | 11696 | 2023-02-08 19:15 | 2023-02-13 17:00 | 4.9062 | N/A | N/A | N/A | N/A | 25.5833
14 | 601 | KHUFF-A2465D | 2022-05-03 | 2022-05-05 10:30 | 2.4375 | 1867 | 2022-05-05 10:30 | 2022-05-07 04:45 | 1.7604 | 2022-05-07 04:45 | 2022-05-09 11:30 | 2.2812 | 3445 | 2022-05-09 11:30 | 2022-05-12 02:30 | 2.625 | 2022-05-12 02:30 | 2022-05-21 11:00 | 9.3542 | 7840 | 2022-05-21 11:00 | 2022-05-25 02:30 | 3.6458 | 2022-05-25 02:30 | 2022-05-27 01:45 | 1.9688 | 9662 | 2022-05-27 01:45 | 2022-05-30 21:00 | 3.8021 | 2022-05-30 21:00 | 2022-06-02 10:15 | 2.5521 | 12120 | 2022-06-02 10:15 | 2022-06-05 18:15 | 3.3333 | N/A | N/A | N/A | N/A | 22.1042
15 | 601 | KHUFF-A2466 | 2022-09-07 06:45 | 2022-09-11 13:15 | 4.2708 | 1804 | 2022-09-11 13:15 | 2022-09-13 09:45 | 1.8542 | 2022-09-13 09:45 | 2022-09-16 06:30 | 2.8646 | 3433 | 2022-09-16 06:30 | 2022-09-19 05:30 | 2.9583 | 2022-09-19 05:30 | 2022-09-29 17:00 | 10.4792 | 7900 | 2022-09-29 17:00 | 2022-10-04 10:00 | 4.7083 | 2022-10-04 10:00 | 2022-10-07 02:45 | 2.6979 | 9857 | 2022-10-07 02:45 | 2022-10-11 08:00 | 4.2188 | 2022-10-11 08:00 | 2022-10-15 03:30 | 3.8125 | 12367 | 2022-10-15 03:30 | 2022-10-21 08:00 | 6.1875 | N/A | N/A | N/A | N/A | 27.1354
16 | 601 | KHUFF-A2621 | 2022-10-30 05:30 | 2022-11-02 12:45 | 3.3021 | 1602 | 2022-11-02 12:45 | 2022-11-16 04:30 | 13.6562 | 2022-11-16 04:30 | 2022-11-18 10:30 | 2.25 | 3119 | 2022-11-18 10:30 | 2022-11-24 18:00 | 6.3125 | 2022-11-24 18:00 | 2022-12-03 16:30 | 8.9375 | 7986 | 2022-12-03 16:30 | 2022-12-08 | 4.3125 | 2022-12-08 | 2022-12-12 17:45 | 4.7396 | 10300 | 2022-12-12 17:45 | 2022-12-16 19:45 | 4.0833 | 2022-12-16 19:45 | 2022-12-23 08:00 | 6.5104 | 13935 | 2022-12-23 08:00 | 2022-12-27 08:30 | 4.0208 | N/A | N/A | N/A | N/A | 38.7708
17 | 602 | KHUFF-A1763 | 2021-02-14 23:00 | 2021-02-18 17:15 | 3.7604 | 1627 | 2021-02-18 17:15 | 2021-02-25 02:00 | 6.3646 | 2021-02-25 02:00 | 2021-02-28 11:15 | 3.3854 | 3070 | 2021-02-28 11:15 | 2021-03-04 19:15 | 4.3333 | 2021-03-04 19:15 | 2021-03-10 19:45 | 6.0208 | 7366 | 2021-03-10 19:45 | 2021-03-16 20:00 | 6.0104 | 2021-03-16 20:00 | 2021-03-24 01:30 | 7.2292 | 9100 | 2021-03-24 01:30 | 2021-03-28 14:15 | 4.5312 | 2021-03-28 14:15 | 2021-03-31 05:30 | 2.6354 | 11570 | 2021-03-31 05:30 | 2021-04-08 | 7.7708 | N/A | N/A | N/A | N/A | 29.875
18 | 602 | KHUFF-A1765 | 2021-11-26 08:15 | 2021-11-29 23:30 | 3.6354 | 1585 | 2021-11-29 23:30 | 2021-12-02 00:15 | 2.0312 | 2021-12-02 00:15 | 2021-12-04 11:30 | 2.4688 | 3148 | 2021-12-04 11:30 | 2021-12-07 18:30 | 3.2917 | 2021-12-07 18:30 | 2021-12-13 10:15 | 5.6562 | 7370 | 2021-12-13 10:15 | 2021-12-17 22:15 | 4.5 | 2021-12-17 22:15 | 2021-12-19 05:00 | 1.2812 | 8748 | 2021-12-19 05:00 | 2021-12-22 16:00 | 3.4583 | 2021-12-22 16:00 | 2021-12-24 18:00 | 2.0833 | 11140 | 2021-12-24 18:00 | 2021-12-29 03:00 | 4.375 | N/A | N/A | N/A | N/A | 21.5833
19 | 602 | KHUFF-A1972 | 2021-04-22 10:15 | 2021-04-25 20:00 | 3.4062 | 1513 | 2021-04-25 20:00 | 2021-05-01 01:00 | 5.2083 | 2021-05-01 01:00 | 2021-05-14 09:15 | 13.3438 | 2401 | 2021-05-14 09:15 | 2021-05-31 05:00 | 16.8229 | 2021-05-31 05:00 | 2021-06-06 10:00 | 6.2083 | 7220 | 2021-06-06 10:00 | 2021-06-10 21:00 | 4.4583 | 2021-06-10 21:00 | 2021-06-13 11:00 | 2.5833 | 8970 | 2021-06-13 11:00 | 2021-06-18 09:45 | 4.9479 | 2021-06-18 09:45 | 2021-06-20 10:00 | 2.0104 | 11265 | 2021-06-20 10:00 | 2021-06-26 22:15 | 6.5104 | N/A | N/A | N/A | N/A | 49.4479
20 | 602 | KHUFF-A2130 | 2020-08-15 00:15 | 2020-08-18 02:45 | 3.1042 | 1748 | 2020-08-18 02:45 | 2020-08-23 10:30 | 5.3229 | 2020-08-23 10:30 | 2020-08-26 14:00 | 3.1458 | 3250 | 2020-08-26 14:00 | 2020-09-04 | 8.4167 | 2020-09-04 | 2020-09-08 23:30 | 4.9792 | 7498 | 2020-09-08 23:30 | 2020-09-16 00:15 | 7.0312 | 2020-09-16 00:15 | 2020-09-18 15:15 | 2.625 | 9210 | 2020-09-18 15:15 | 2020-09-28 20:45 | 10.2292 | 2020-09-28 20:45 | 2020-10-07 17:30 | 8.8646 | 11586 | 2020-10-06 02:00 | 2020-10-10 15:45 | 4.5729 | N/A | N/A | N/A | N/A | 32
21 | 602 | KHUFF-A2146 | 2021-07-10 09:15 | 2021-07-15 04:00 | 4.7812 | 1988 | 2021-07-15 04:00 | 2021-07-25 05:15 | 10.0521 | 2021-07-25 05:15 | 2021-07-30 06:00 | 5.0312 | 3770 | 2021-07-30 06:00 | 2021-08-04 12:15 | 5.2604 | 2021-08-04 12:15 | 2021-08-15 20:45 | 11.3542 | 8430 | 2021-08-15 20:45 | 2021-08-22 00:30 | 6.1562 | 2021-08-22 00:30 | 2021-08-24 21:45 | 2.8854 | 10520 | 2021-08-24 21:45 | 2021-08-29 15:30 | 4.7396 | 2021-08-29 15:30 | 2021-09-01 01:15 | 2.4062 | 12180 | 2021-09-01 01:15 | 2021-09-10 01:15 | 9 | N/A | N/A | N/A | N/A | 42.6354
22 | 602 | KHUFF-A2148 | 2022-01-08 16:00 | 2022-01-12 05:00 | 3.5417 | 1549 | 2022-01-12 05:00 | 2022-01-14 22:00 | 2.7083 | 2022-01-14 22:00 | 2022-01-16 13:45 | 1.6562 | 2511 | 2022-01-16 13:45 | 2022-01-24 02:00 | 7.5104 | 2022-01-24 02:00 | 2022-01-30 13:30 | 6.4792 | 7658 | 2022-01-30 13:30 | 2022-02-04 07:00 | 4.7292 | 2022-02-04 07:00 | 2022-02-06 17:00 | 2.4167 | 9530 | 2022-02-06 17:00 | 2022-02-10 14:15 | 3.8854 | 2022-02-10 14:15 | 2022-02-13 19:15 | 3.2083 | 11800 | 2022-02-13 19:15 | 2022-02-20 02:30 | 6.3021 | N/A | N/A | N/A | N/A | 26.625
23 | 602 | KHUFF-A2233 | 2021-10-01 02:30 | 2021-10-04 15:30 | 3.5417 | 1631 | 2021-10-04 15:30 | 2021-10-07 02:45 | 2.4688 | 2021-10-07 02:45 | 2021-10-10 10:00 | 3.3021 | 3145 | 2021-10-10 10:00 | 2021-10-14 16:30 | 4.2708 | 2021-10-14 16:30 | 2021-10-20 11:00 | 5.7708 | 7845 | 2021-10-20 11:00 | 2021-10-25 17:30 | 5.2708 | 2021-10-25 17:30 | 2021-10-28 05:15 | 2.4896 | 9833 | 2021-10-28 05:15 | 2021-11-01 22:00 | 4.6979 | 2021-11-01 22:00 | 2021-11-05 00:30 | 3.1042 | 12247 | 2021-11-05 00:30 | 2021-11-10 22:00 | 5.8958 | N/A | N/A | N/A | N/A | 24.625
24 | 602 | KHUFF-A2235 | 2020-11-03 02:00 | 2020-11-06 15:00 | 3.5417 | 1518 | 2020-11-06 15:00 | 2020-11-10 12:15 | 3.8854 | 2020-11-10 12:15 | 2020-11-13 10:00 | 2.9062 | 2889 | 2020-11-13 10:00 | 2020-11-18 06:00 | 4.8333 | 2020-11-18 06:00 | 2020-11-24 05:30 | 5.9792 | 7144 | 2020-11-24 05:30 | 2020-12-02 23:15 | 8.7396 | 2020-12-02 23:15 | 2020-12-05 02:00 | 2.1146 | 8662 | 2020-12-05 02:00 | 2020-12-13 11:45 | 8.4062 | 2020-12-13 11:45 | 2020-12-16 04:15 | 2.6875 | 10757 | 2020-12-16 04:15 | 2020-12-21 16:30 | 5.5104 | N/A | N/A | N/A | N/A | 29.8854
25 | 602 | KHUFF-A2408 | 2022-03-02 08:30 | 2022-03-06 11:00 | 4.1042 | 1805 | 2022-03-06 11:00 | 2022-03-08 15:30 | 2.1875 | 2022-03-08 15:30 | 2022-03-13 03:00 | 4.4792 | 3559 | 2022-03-13 03:00 | 2022-03-18 00:15 | 4.8854 | 2022-03-18 00:15 | 2022-03-27 03:30 | 9.1354 | 7932 | 2022-03-27 03:30 | 2022-03-30 22:45 | 3.8021 | 2022-03-30 22:45 | 2022-04-02 16:00 | 2.7188 | 9745 | 2022-04-02 16:00 | 2022-04-06 06:00 | 3.5833 | 2022-04-06 06:00 | 2022-04-08 19:30 | 2.5625 | 12218 | 2022-04-08 19:30 | 2022-04-12 08:45 | 3.5521 | N/A | N/A | N/A | N/A | 28.5938
26 | 602 | PU-0001 | 2019-10-25 19:00 | 2019-10-28 10:30 | 2.6458 | 1521 | 2019-10-28 10:30 | 2019-11-03 19:00 | 6.3542 | 2019-11-03 19:00 | 2019-11-05 21:30 | 2.1042 | 2984 | 2019-11-05 21:30 | 2019-11-12 16:00 | 6.7708 | 2019-11-12 16:00 | 2019-11-18 08:30 | 5.6875 | 7084 | 2019-11-18 08:30 | 2019-11-24 10:30 | 6.0833 | 2019-11-24 10:30 | 2019-11-25 17:45 | 1.3021 | 8352 | 2019-11-25 17:45 | 2019-11-29 23:30 | 4.2396 | 2019-11-29 23:30 | 2019-12-03 02:00 | 3.1042 | 10715 | 2019-12-03 02:00 | 2019-12-07 22:45 | 4.8646 | 2019-12-07 22:45 | 2020-02-28 05:30 | 82.2812 | 12827 | 29.6458 | 13.5104
27 | 601 | PU-0004 | 2019-11-11 05:00 | 2019-11-13 18:15 | 2.5521 | 1525 | 2019-11-13 18:15 | 2019-11-21 14:15 | 7.8333 | 2019-11-21 14:15 | 2019-11-25 07:00 | 3.6979 | 2900 | 2019-11-25 07:00 | 2019-11-29 17:30 | 4.4375 | 2019-11-29 17:30 | 2019-12-05 18:00 | 6.0208 | 7092 | 2019-12-05 18:00 | 2019-12-10 20:00 | 5.0833 | 2019-12-10 20:00 | 2019-12-12 22:30 | 2.1042 | 8736 | 2019-12-12 22:30 | 2019-12-17 13:00 | 4.6042 | 2019-12-17 13:00 | 2019-12-23 15:30 | 6.1042 | 10940 | 2019-12-23 15:30 | 2020-01-08 10:45 | 15.8021 | 2020-01-08 10:45 | 2020-02-05 02:45 | 27.6667 | 12530 | 29.625 | 28.6146
28 | 602 | PU-0003 | 2022-04-23 14:15 | 2022-04-27 11:00 | 3.8646 | 1635.46 | 2022-04-27 11:00 | 2022-04-29 17:45 | 2.2812 | 2022-04-29 17:45 | 2022-05-02 13:15 | 2.8125 | 3090 | 2022-05-02 13:15 | 2022-05-05 15:45 | 3.1042 | 2022-05-05 15:45 | 2022-05-12 05:00 | 6.5521 | 7277 | 2022-05-12 05:00 | 2022-05-15 23:15 | 3.7604 | 2022-05-15 23:15 | 2022-06-08 02:15 | 23.125 | 11195 | 2022-06-08 02:15 | 2022-06-12 20:15 | 4.75 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2022-06-12 20:15 | 2022-06-16 10:30 | 3.5938 | 12210 | 22.375 | 27.875
29 | 602 | PU-0005 | 2022-07-06 14:00 | 2022-07-10 14:00 | 4 | 1505.26 | 2022-07-10 14:00 | 2022-07-12 20:00 | 2.25 | 2022-07-12 20:00 | 2022-07-15 03:30 | 2.3125 | 2847 | 2022-07-15 03:30 | 2022-07-18 09:15 | 3.2396 | 2022-07-18 09:15 | 2022-07-24 04:15 | 5.7917 | 7047 | 2022-07-24 04:15 | 2022-07-27 22:00 | 3.7396 | 2022-07-27 22:00 | 2022-08-12 21:30 | 15.9792 | 11100 | 2022-08-12 21:30 | 2022-08-23 03:45 | 10.2604 | 2022-08-23 03:45 | 2022-09-02 10:00 | 10.2604 | 13230 | 2022-09-02 10:00 | 2022-09-18 02:15 | 15.6771 | N/A | N/A | N/A | N/A | 21.3333
30 | 602 | PU-0006 | 2022-10-09 00:15 | 2022-10-13 07:00 | 4.2812 | 1525 | 2022-10-13 07:00 | 2022-10-15 19:00 | 2.5 | 2022-10-15 19:00 | 2022-10-18 17:45 | 2.9479 | 2875 | 2022-10-18 17:45 | 2022-10-22 12:15 | 3.7708 | 2022-10-22 12:15 | 2022-11-07 08:30 | 15.8438 | 6965 | 2022-11-07 08:30 | 2022-11-11 08:45 | 4.0104 | 2022-11-11 08:45 | 2022-12-01 01:00 | 19.6771 | 10790 | 2022-12-01 01:00 | 2022-12-08 08:30 | 7.3125 | 2022-12-08 08:30 | 2022-12-17 22:45 | 9.5938 | 12320 | 2022-12-17 22:45 | 2022-12-23 10:30 | 5.4896 | N/A | N/A | N/A | N/A | 33.3542
31 | 601 | PU-0009 | 2023-02-22 22:00 | 2023-02-25 23:30 | 3.0625 | 1642 | 2023-02-25 23:30 | 2023-02-27 16:45 | 1.7188 | 2023-02-27 16:45 | 2023-03-02 07:30 | 2.6146 | 3127 | 2023-03-02 07:30 | 2023-03-05 12:00 | 3.1875 | 2023-03-05 12:00 | 2023-03-11 07:30 | 5.8125 | 7427 | 2023-03-11 07:30 | 2023-03-15 09:45 | 4.0938 | 2023-03-15 09:45 | 2023-03-31 01:45 | 15.6667 | 11513 | 2023-03-31 01:45 | 2023-04-09 01:30 | 8.9896 | 2023-04-09 01:30 | 2023-05-06 07:00 | 27.2292 | 11875 | 2023-05-06 07:00 | 2023-05-12 06:00 | 5.9583 | 2023-05-12 06:00 | 2023-05-31 18:30 | 19.5208 | 17550 | 20.4896 | 57.8438
32 | 602 | PU-0002 | 2023-03-22 20:15 | 2023-03-26 11:30 | 3.6354 | 1578.28 | 2023-03-26 11:30 | 2023-03-29 00:15 | 2.5312 | 2023-03-29 00:15 | 2023-03-30 23:30 | 1.9688 | 3035 | 2023-03-30 23:30 | 2023-04-03 03:30 | 3.1667 | 2023-04-03 03:30 | 2023-04-08 13:45 | 5.4271 | 7240 | 2023-04-08 13:45 | 2023-04-12 09:15 | 3.8125 | 2023-04-12 09:15 | 2023-05-04 11:30 | 22.0938 | 11285 | 2023-05-04 11:30 | 2023-05-09 12:45 | 5.0521 | 2023-05-09 12:45 | 2023-05-14 17:00 | 5.1771 | 13264 | 2023-05-14 17:00 | 2023-05-27 09:15 | 12.6771 | N/A | N/A | N/A | N/A | 20.5417
33 | 602 | PU-0011 | 2023-06-08 16:45 | 2023-06-11 23:30 | 3.2812 | 1512 | 2023-06-11 23:30 | 2023-06-14 00:15 | 2.0312 | 2023-06-14 00:15 | 2023-06-16 13:00 | 2.5312 | 2881 | 2023-06-16 13:00 | 2023-06-20 12:15 | 3.9688 | 2023-06-20 12:15 | 2023-06-25 11:15 | 4.9583 | 7158 | 2023-06-25 11:15 | 2023-06-29 12:15 | 4.0417 | 2023-06-29 12:15 | 2023-07-16 21:45 | 17.3958 | 10890 | 2023-07-16 21:45 | 2023-07-22 02:30 | 5.1979 | 2023-07-22 02:30 | 2023-07-25 11:00 | 3.3542 | 12320 | 2023-07-25 11:00 | 2023-08-03 03:15 | 8.6771 | N/A | N/A | N/A | N/A | 20.8125
34 | 601 | PU-0007 | 2023-06-16 06:00 | 2023-06-18 20:30 | 2.6042 | 1548 | 2023-06-18 20:30 | 2023-06-20 13:30 | 1.7083 | 2023-06-20 13:30 | 2023-06-22 21:00 | 2.3125 | 2932 | 2023-06-22 21:00 | 2023-06-27 15:45 | 4.7812 | 2023-06-27 15:45 | 2023-07-04 17:15 | 7.0625 | 7057 | 2023-07-04 17:15 | 2023-07-09 01:45 | 4.3542 | 2023-07-09 01:45 | 2023-08-01 21:00 | 23.8021 | 11260 | 2023-08-01 21:00 | 2023-08-06 09:30 | 4.5208 | 2023-08-06 09:30 | 2023-08-11 08:00 | 4.9375 | 13100 | 2023-08-11 08:00 | 2023-08-17 04:15 | 5.8438 | N/A | N/A | N/A | N/A | 22.8229
35 | 602 | PU-0012 | 2023-08-14 19:15 | 2023-08-17 09:45 | 2.6042 | 1546.15 | 2023-08-17 09:45 | 2023-08-19 12:15 | 2.1042 | 2023-08-19 12:15 | 2023-08-21 20:15 | 2.3333 | 2922 | 2023-08-21 20:15 | 2023-08-24 23:00 | 3.1146 | 2023-08-24 23:00 | 2023-08-29 17:45 | 4.7812 | 7170 | 2023-08-29 17:45 | 2023-09-02 14:15 | 3.8542 | 2023-09-02 14:15 | 2023-09-20 14:00 | 17.9896 | 10830 | 2023-09-20 14:00 | 2023-09-25 21:00 | 5.2917 | 2023-09-25 21:00 | 2023-09-30 00:45 | 4.1562 | 12382 | 2023-09-30 00:45 | 2023-10-09 13:00 | 9.5104 | N/A | N/A | N/A | N/A | 18.7917
36 | 601 | PU-0014 | 2023-08-25 13:00 | 2023-08-28 22:15 | 3.3854 | 1507 | 2023-08-28 22:15 | 2023-08-30 20:45 | 1.9375 | 2023-08-30 20:45 | 2023-09-01 19:45 | 1.9583 | 2947 | 2023-09-01 19:45 | 2023-09-05 00:30 | 3.1979 | 2023-09-05 00:30 | 2023-09-10 02:30 | 5.0833 | 7058 | 2023-09-10 02:30 | 2023-09-13 21:00 | 3.7708 | 2023-09-13 21:00 | 2023-10-01 20:30 | 17.9792 | 10762 | 2023-10-01 20:30 | 2023-10-08 14:00 | 6.7292 | 2023-10-08 14:00 | 2023-10-12 06:00 | 3.6667 | 12236 | 2023-10-12 06:00 | 2023-10-17 04:00 | 4.9167 | 2023-10-17 04:00 | 2023-10-20 23:30 | 3.8125 | 14075 | 19.3333 | 33.2917
37 | 602 | PU-0013 | 2023-10-24 07:00 | 2023-10-27 18:15 | 3.4688 | 1638 | 2023-10-27 18:15 | 2023-10-29 10:00 | 1.6562 | 2023-10-29 10:00 | 2023-10-31 16:30 | 2.2708 | 3201 | 2023-10-31 16:30 | 2023-11-03 10:45 | 2.7604 | 2023-11-03 10:45 | 2023-11-07 10:30 | 3.9896 | 7535 | 2023-11-07 10:30 | 2023-11-11 11:00 | 4.0208 | 2023-11-11 11:00 | 2023-12-05 06:00 | 23.7917 | 11815 | 2023-12-05 06:00 | 2023-12-11 06:30 | 6.0208 | 2023-12-11 06:30 | 2023-12-16 02:45 | 4.8438 | 13970 | 2023-12-16 02:45 | 2023-12-29 01:00 | 12.9271 | 2023-12-29 01:00 | 2024-01-16 16:45 | 18.6562 | 16000 | 18.1667 | 47.5833
38 | 601 | PU-0015 | 2024-01-05 13:00 | 2024-01-07 13:30 | 2.0208 | 1552 | 2024-01-07 13:30 | 2024-01-09 10:45 | 1.8854 | 2024-01-09 10:45 | 2024-01-11 11:30 | 2.0312 | 2990 | 2024-01-11 11:30 | 2024-01-15 03:00 | 3.6458 | 2024-01-15 03:00 | 2024-01-21 09:15 | 6.2604 | 7121 | 2024-01-21 09:15 | 2024-01-24 19:30 | 3.4271 | 2024-01-24 19:30 | 2024-02-11 01:45 | 17.2604 | 11040 | 2024-02-11 01:45 | 2024-02-15 04:45 | 4.125 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-02-15 04:45 | 2024-02-17 20:15 | 2.6458 | 12710 | 19.2708 | 21.3854
39 | 602 | PU-0016 | 2024-02-08 11:30 | 2024-02-10 23:00 | 2.4792 | 1625 | 2024-02-10 23:00 | 2024-02-12 22:00 | 1.9583 | 2024-02-12 22:00 | 2024-02-14 18:15 | 1.8438 | 3190 | 2024-02-14 18:15 | 2024-02-17 18:15 | 3 | 2024-02-17 18:15 | 2024-02-23 04:45 | 5.4375 | 7360 | 2024-02-23 04:45 | 2024-02-26 08:45 | 3.1667 | 2024-02-26 08:45 | 2024-03-14 13:30 | 17.1979 | 11131 | 2024-03-14 13:30 | 2024-03-18 17:15 | 4.1562 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-03-18 17:15 | 2024-03-23 12:45 | 4.8125 | 12940 | 17.8854 | 21.3542
40 | 601 | PU-0008 | 2024-02-29 17:45 | 2024-03-02 01:45 | 1.3333 | 1520 | 2024-03-02 01:45 | 2024-03-03 14:45 | 1.5417 | 2024-03-03 15:30 | 2024-03-05 09:15 | 1.7396 | 2874 | 2024-03-05 09:15 | 2024-03-10 10:45 | 5.0625 | 2024-03-10 10:45 | 2024-03-15 03:30 | 4.6979 | 6975 | 2024-03-15 03:30 | 2024-03-18 08:00 | 3.1875 | 2024-03-18 08:00 | 2024-03-19 06:00 | 0.91667 | 8260 | 2024-03-19 06:00 | 2024-03-23 09:15 | 4.1354 | 2024-03-23 09:15 | 2024-03-25 21:00 | 2.4896 | 10900 | 2024-03-25 21:00 | 2024-03-29 22:00 | 4.0417 | 2024-03-29 22:00 | 2024-03-31 17:45 | 1.8229 | 12792 | 17.5938 | 11.5833
41 | 602 | PU-0010 | 2024-04-08 18:30 | 2024-04-10 11:30 | 1.7083 | 1520 | 2024-04-10 11:30 | 2024-04-13 13:15 | 3.0729 | 2024-04-13 13:15 | 2024-04-15 | 1.4479 | 2858 | 2024-04-15 | 2024-04-18 07:15 | 3.3021 | 2024-04-18 07:15 | 2024-04-20 03:30 | 1.8438 | 7060 | 2024-04-20 03:30 | 2024-04-24 05:00 | 4.0625 | 2024-05-30 17:15 | 2024-06-02 16:45 | 2.9792 | 8350 | 2024-06-02 16:45 | 2024-06-08 13:00 | 5.8438 | 2024-06-08 13:00 | 2024-06-10 06:00 | 1.7083 | 10820 | 2024-06-10 06:00 | 2024-06-13 22:30 | 3.6875 | 2024-06-13 22:30 | 2024-06-15 04:45 | 1.2604 | 12146 | 51.9479 | 14.2188
42 | 601 | PU-0017 | 2024-04-13 | 2024-04-14 07:45 | 1.3229 | 1620 | 2024-04-14 07:45 | 2024-04-16 11:30 | 2.1562 | 2024-04-16 11:30 | 2024-04-18 11:15 | 1.9896 | 3112 | 2024-04-18 11:15 | 2024-04-23 05:00 | 4.7396 | 2024-04-23 05:00 | 2024-04-26 01:30 | 2.8542 | 7256 | 2024-04-26 01:30 | 2024-04-30 09:00 | 4.3125 | 2024-04-30 09:00 | 2024-05-01 06:30 | 0.89583 | 8762 | 2024-05-01 06:30 | 2024-05-04 15:00 | 3.3542 | 2024-05-04 15:00 | 2024-05-14 10:30 | 9.8125 | 11220 | 2024-05-14 10:30 | 2024-05-20 06:30 | 5.8333 | 2024-05-20 06:30 | 2024-05-31 06:30 | 11 | 17008 | 17.375 | 19.8958
43 | 601 | PU-0020 | 2024-06-22 14:00 | 2024-06-24 10:30 | 1.8542 | 1512 | 2024-06-24 10:30 | 2024-06-28 04:15 | 3.7396 | 2024-06-28 04:15 | 2024-06-29 10:00 | 1.2396 | 3017 | 2024-06-29 10:00 | 2024-07-04 01:00 | 4.625 | 2024-07-04 01:00 | 2024-07-06 22:00 | 2.875 | 7257 | 2024-07-06 22:00 | 2024-07-10 05:45 | 3.3229 | 2024-07-10 05:45 | 2024-07-11 10:45 | 1.2083 | 8852 | 2024-07-11 10:45 | 2024-07-14 18:15 | 3.3125 | 2024-07-14 18:15 | 2024-07-18 03:15 | 3.375 | 11216 | 2024-07-18 03:15 | 2024-07-20 12:00 | 2.3646 | 2024-07-20 12:00 | 2024-07-23 08:15 | 2.8438 | 13018 | 17.6562 | 10.2604
44 | 602 | PU-0018 | 2024-07-31 | 2024-08-02 05:30 | 2.2292 | 1529 | 2024-08-02 05:30 | 2024-08-07 08:00 | 5.1042 | 2024-08-07 08:00 | 2024-08-09 06:30 | 1.9375 | 2961 | 2024-08-09 06:30 | 2024-08-12 09:00 | 3.1042 | 2024-08-12 09:00 | 2024-08-14 08:30 | 1.9792 | 7132 | 2024-08-14 08:30 | 2024-08-18 18:30 | 4.4167 | 2024-08-18 18:30 | 2024-08-21 14:00 | 2.8125 | 8864 | 2024-08-21 14:00 | 2024-08-29 04:30 | 7.6042 | 2024-08-29 04:30 | 2024-09-01 15:00 | 3.4375 | 11225 | 2024-09-01 15:00 | 2024-09-04 11:00 | 2.8333 | 2024-09-04 11:00 | 2024-09-09 05:30 | 4.7708 | 13175 | 18.7708 | 16.6875
45 | 601 | TRF-2 | 2024-08-05 14:00 | 2024-08-07 20:45 | 2.2812 | 1445 | 2024-08-07 20:45 | 2024-08-09 22:45 | 2.0833 | 2024-08-09 22:45 | 2024-08-11 04:00 | 1.2188 | 2672 | 2024-08-11 04:00 | 2024-08-14 01:45 | 2.9062 | 2024-08-14 01:45 | 2024-08-19 16:15 | 5.6042 | 6232 | 2024-08-19 16:15 | 2024-08-23 00:30 | 3.3438 | 2024-08-23 00:30 | 2024-08-30 02:45 | 7.0938 | 8349 | 2024-08-30 02:45 | 2024-09-02 11:00 | 3.3438 | 2024-09-02 11:00 | 2024-10-24 02:30 | 51.6458 | 15981 | 2024-10-24 02:30 | 2024-10-27 02:00 | 2.9792 | 2024-10-27 02:00 | 2024-10-31 15:30 | 4.5625 | 16322 | 17.4375 | 65.0625
46 | 602 | PU-0019 | 2024-09-24 05:00 | 2024-09-25 23:30 | 1.7708 | 1564 | 2024-09-25 23:30 | 2024-09-29 15:30 | 3.6667 | 2024-09-29 15:30 | 2024-10-18 18:00 | 19.1042 | 2904 | 2024-10-18 18:00 | 2024-10-21 16:00 | 2.9167 | 2024-10-21 16:00 | 2024-10-24 12:30 | 2.8542 | 7152 | 2024-10-24 12:30 | 2024-10-27 15:30 | 3.125 | 2024-10-27 15:30 | 2024-10-28 09:00 | 0.72917 | 8513 | 2024-10-28 09:00 | 2024-10-30 19:30 | 2.4375 | 2024-10-30 19:30 | 2024-11-01 11:45 | 1.6771 | 10716 | 2024-11-01 11:45 | 2024-11-04 | 2.5104 | 2024-11-04 | 2024-11-30 18:45 | 26.7812 | 12520 | 33.4375 | 7.3542
47 | 601 | PU-0021 | 2024-11-13 03:00 | 2024-11-15 15:00 | 2.5 | 1575 | 2024-11-15 15:00 | 2024-11-17 17:15 | 2.0938 | 2024-11-17 17:15 | 2024-11-19 07:00 | 1.5729 | 3123 | 2024-11-19 07:00 | 2024-11-22 14:45 | 3.3229 | 2024-11-22 14:45 | 2024-11-25 08:30 | 2.7396 | 7315 | 2024-11-25 08:30 | 2024-11-28 17:30 | 3.375 | 2024-11-28 17:30 | 2024-12-02 11:30 | 3.75 | 8636 | 2024-12-02 11:30 | 2024-12-07 06:45 | 4.8021 | 2024-12-07 06:45 | 2024-12-08 17:00 | 1.4271 | 11108 | 2024-12-08 17:00 | 2024-12-11 19:45 | 3.1146 | 2024-12-11 19:45 | 2025-01-06 15:30 | 25.8229 | 17552 | 15.6042 | 13.0938
48 | 601 | PU-0024 | 2025-01-24 12:45 | 2025-01-25 23:00 | 1.4271 | 1581 | 2025-01-25 23:00 | 2025-01-28 03:30 | 2.1875 | 2025-01-28 03:30 | 2025-01-29 14:00 | 1.4375 | 3075 | 2025-01-29 14:00 | 2025-02-02 00:30 | 3.4375 | 2025-02-02 00:30 | 2025-02-04 13:00 | 2.5208 | 7250 | 2025-02-04 13:00 | 2025-02-07 22:00 | 3.375 | 2025-02-07 22:00 | 2025-02-10 20:30 | 2.9375 | 8670 | 2025-02-10 20:30 | 2025-02-14 13:30 | 3.7083 | 2025-02-14 13:30 | 2025-02-17 19:15 | 3.2396 | 11317 | 2025-02-17 19:15 | 2025-02-20 22:00 | 3.1146 | 2025-02-20 22:00 | 2025-02-22 16:15 | 1.7604 | 13085 | 14.3854 | 13
49 | 602 | PU-0022 | 2025-01-25 03:30 | 2025-01-26 17:15 | 1.5729 | 1599 | 2025-01-26 17:15 | 2025-01-28 17:45 | 2.0208 | 2025-01-28 17:45 | 2025-01-30 12:00 | 1.7604 | 3100 | 2025-01-30 12:00 | 2025-02-02 07:45 | 2.8229 | 2025-02-02 07:45 | 2025-02-05 13:45 | 3.25 | 7237 | 2025-02-05 13:45 | 2025-02-08 12:15 | 2.9375 | 2025-02-08 12:15 | 2025-02-09 23:30 | 1.4688 | 8550 | 2025-02-09 23:30 | 2025-02-13 06:15 | 3.2812 | 2025-02-13 06:15 | 2025-02-15 01:00 | 1.7812 | 11142 | 2025-02-15 01:00 | 2025-02-17 12:30 | 2.4792 | 2025-02-17 12:30 | 2025-02-18 21:00 | 1.3542 | 12805 | 14.3646 | 9.0104
50 | 602 | A-2837 | 2025-02-28 17:00 | 2025-03-01 20:45 | 1.1562 | 1766 | 2025-03-01 20:45 | 2025-03-02 14:15 | 0.72917 | N/A | N/A | 0 | 1766 | 2025-03-02 14:15 | 2025-03-04 13:00 | 1.9479 | 2025-03-04 13:00 | 2025-03-08 13:30 | 4.0208 | 7540 | 2025-03-08 13:30 | 2025-03-12 17:45 | 4.1771 | 2025-03-12 17:45 | 2025-03-15 18:30 | 3.0312 | 9200 | 2025-03-15 18:30 | 2025-03-20 04:30 | 4.4167 | 2025-03-20 04:30 | 2025-03-28 15:00 | 8.4375 | 11738 | 2025-03-28 15:00 | 2025-03-31 12:30 | 2.8958 | 2025-03-31 12:30 | 2025-04-17 15:45 | 17.1354 | 14864 | 12.0312 | 18.7812
51 | 601 | A-2836 | 2025-04-21 16:00 | 2025-04-23 09:15 | 1.7188 | 1532 | 2025-04-23 09:15 | 2025-04-25 13:00 | 2.1562 | 2025-04-25 13:00 | 2025-04-26 23:30 | 1.4375 | 2950 | 2025-04-26 23:30 | 2025-04-30 21:00 | 3.8958 | 2025-04-30 21:00 | 2025-05-06 23:00 | 6.0833 | 7822 | 2025-05-06 23:00 | 2025-05-10 20:45 | 3.9062 | 2025-05-10 20:45 | 2025-05-14 03:00 | 3.2604 | 9832 | 2025-05-14 03:00 | 2025-05-17 02:15 | 2.9688 | 2025-05-17 02:15 | 2025-05-19 15:45 | 2.5625 | 12445 | 2025-05-19 15:45 | 2025-05-24 09:30 | 4.7396 | N/A | N/A | N/A | N/A | 19.1979
52 | 602 | A-2838 | 2025-05-03 11:30 | 2025-05-05 00:15 | 1.5312 | 1655 | 2025-05-05 00:15 | 2025-05-05 14:15 | 0.58333 | N/A | N/A | N/A | N/A | 2025-05-05 14:15 | 2025-05-06 12:15 | 0.91667 | 2025-05-06 12:15 | 2025-05-11 14:15 | 5.0833 | 7715 | 2025-05-11 14:15 | 2025-05-15 13:30 | 3.9688 | 2025-05-15 13:30 | 2025-05-18 18:45 | 3.2188 | 10195 | 2025-05-18 18:45 | 2025-05-21 17:45 | 2.9583 | 2025-05-21 17:45 | 2025-05-23 12:00 | 1.7604 | 11470 | 2025-05-23 12:00 | 2025-05-27 12:45 | 4.0312 | 2025-05-27 12:45 | 2025-05-29 13:15 | 2.0208 | 13350 | 12.0833 | 11.9688
53 | 602 | EOG J1 | 2025-06-09 23:00 | 2025-06-11 05:00 | 1.25 | 1724 | 2025-06-11 05:00 | 2025-06-13 02:00 | 1.875 | 2025-06-13 02:00 | 2025-06-14 19:15 | 1.7188 | 3196 | 2025-06-14 19:15 | 2025-06-19 06:00 | 4.4479 | 2025-06-19 06:00 | 2025-06-22 13:00 | 3.2917 | 7435 | 2025-06-22 13:00 | 2025-06-28 23:45 | 6.4479 | 2025-06-28 23:45 | 2025-06-30 18:15 | 1.7708 | 9095 | 2025-06-30 18:15 | 2025-07-05 06:15 | 4.5 | 2025-07-05 06:15 | 2025-07-09 03:30 | 3.8854 | 12833 | 2025-07-09 03:30 | 2025-07-22 22:45 | 13.8021 | 2025-07-22 22:45 | 2025-07-30 11:30 | 7.5312 | 17500 | 19.0312 | 23.9583